**Basic Scheduling**

* A 🡪 B 🡪 E 🡪 H = 8 weeks.
* A 🡪 C 🡪 E 🡪 H = 7 weeks.
* A 🡪 C 🡪 F 🡪 H = 10 weeks.
* A 🡪 D 🡪 G 🡪 H =19 weeks.
* The critical path is 19 weeks (longest path).
* Tasks B, C, and D can be delayed.

3 weeks

1 week

8 weeks

2 weeks

2 weeks

5 weeks

9 weeks

4 weeks

2 weeks

2 weeks

H

G

F

E

D

c

B

A